## Slide 1: Caregiver URMC Project Team
Objectives
Data preprocessing:
  Clean and classify cancer treatments for use as an independent variable
    Deliverable: an algorithm to apply to dataset
Data analysis:
  Develop predictive models for caregiver outcomes such as QoL. Compare these models to the logistic regression models in Kehoe et al paper

## Slide 2: Caregiver URMC Project Team
Achievements
Completed and submitted CITI Training Certifications
Set Box account and gained access to project related document(no data provided yet)
Created Slack Workspace for regular group discussion
Read relevant papers to get a broad understanding of the project

## Slide 3: Caregiver URMC Project Team
Next Steps
sign data user agreement
start exploratory analysis
finish first part (data cleaning) of the project
discuss which models are good for prediction

## Slide 4: Caregiver URMC Project Team
Challenges
waiting on the data